## Sheet1
Risk Mitigation Action – Status Update as of July 2022
NO | Risk | Consequence | Proposed mitigation measures | Implementation | Lead | Planned activities to implement measures | Status
Deadline
1 | Resource constraints arising from failure to attract funding | Inability to fund fixed costs of operations. | Re-engagement with members to improve ownership and member budgetary support | Periodic Annually | ED/B.o.D | ¥ Hold periodic CPM Summits for member's engagement meetings every two years | ¥ CPM held May 2019
¥ CPM Scheduled in Sept 2022
¥ Held PS/DG/BoD Consultative meeting on ASARECA Financial sustainability in Oct 2020
¥ CDG operationalized
¥ Held CDGs meeting June 2021- focus on ASARECA Fin Sustainability
[6 empty] | ¥ Update membership register and recruit new members | ¥ Core members register updated
¥ 2 new core Membership recruited
¥ Update of Register for Ordinary members by Oct 2021
¥ Further member recruitment is ongoing.
[6 empty] | ¥ Activate National Focal Persons(FP), update DGs on ASARECA's work, and Business committees activities coordinated with ASARECA AWPB | ¥ FP appointed for all member countries
¥ FP sensitized on their mandate
¥ FP activity coordinated with ASARECA AWPB
¥ BC meetings are funded periodically
[6 empty] | ¥ B.o.D & management pursue & Collect Membership fees | ¥ B.o.D regularly discuss memberships fee collection
¥ Allocate countries to different board members as key leads to memberships fee collection
¥ Board members are regularly updated on progress on collections
[6 empty] | ¥ Maintain a lean Secretariat & optimum fixed cost | ¥ HR plan submitted and approved by 29th Board emphasizing lean secretariat team MTOP period
¥ Work through Focal person & partners at the country level
¥ The remuneration policy is designed to ensure:
ü ASARECA attracts needed talent
ü PayScale based on the market survey for level cadre & scope of work.
ü Actual pay is based on individual performance & overall affordability and financial status of ASARECA.
¥ The current staff level is planned at 15 staff, including 8 technical programme staff and 7 Fiduciary and Ops support. Outsourced ICT, legal and Procurement roles and use Volunteers as needed
|  | Inability to raise funds for projects | Develop and implement a resource mobilisation strategy | 2020-09-01 | Resource mobilisation team | ¥ Develop and implement a Resource Mobilisation & Sustainability Strategy (RMSS) & Action Plan | ¥ RMSS Strategy & action plan completed by March 2020
¥ Priority Activities identified from Action
¥ Plan
[6 empty] | ¥ Develop Partnership Strategy | ¥ Planned for 2022 AWPB
[6 empty] | ¥ Fund & Implement RMSS action plans | ¥ Dedicated a percentage of staff time for professional-level staff to focus on resource mobilisation technical team
¥ Ongoing implementation of priority action plan
[6 empty] | ¥ Enhance M&E and Impact reporting | ¥ M& E system upgraded and operational
¥ M& E team trained on the use of the new system
¥ Field data collection to start by Q3 2021
¥ Real-time reporting from the M&E system is expected by Jan 2022
|  | Threatened going concern of ASARECA | Re-branding to improve the organisational image to stakeholder | 2020-12-01 | Communication lead | ¥ Update and implement a branding strategy | ¥ Branding strategy updated by December 2019
[6 empty] | ¥ Update and implement a communication strategy | ¥ Communication strategy updated December 2020
[6 empty] | ¥ Integrate system for timely & quality internal and external reporting | ¥ Strategic communication Ongoing
¥ Newsletters, Annual reports, Branded communication products, Online tools deployed, website optimized and regularly updated
¥ K-HUB 1st phase completed and updated in corroboration with stakeholders. Phase 2 is ongoing for completion by 31st December 2021
[5 empty] | Head of Finance | ¥ Update Investment & Reserve policies, and maintain appropriate reserve balance | ¥ Updated reserved policy June 2020
¥ Minimum reserve policy of US$ 1.2m
[5 empty] | ED | ¥ Use of the HLAP, Board, RM Champions and Patron Ministers to negotiate with strategic resource partners | ¥ Ongoing collaboration with members
¥ Engagement of Patron minster(s) esp. the chair to advocate for strategic funding framework
¥ Engaged DGs and line ministers for country-level budgetary support to ASARECA
¥ Country-level visits by HLAP and ASARECA Management.
¦2 | Over-dependence on a limited source of funding | Loss of mission independence | Donor diversification strategy as part of the resource mobilisation strategy. | Ongoing | ED & management team | ¥ Programme and negotiate strategic funding partnerships that fund the strategy as a whole. | ¥ Ongoing work in corroboration with other SROs led by FARA to develop strategic funding proposals for the whole strategy
[6 empty] | ¥ Develop a business case for an MDTF for ASARECA | ¥ Pending work on MDTF Business Case
¥ CAADP XP4 project designed to fund in part ASARECA capacity building to deliver the mandate
¥ Developed and implemented a cost allocation policy to ensure each project contributes a prorate share of fixed and operation costs to avoid subsidising projects.
|  | Vulnerability to external shock linked to the dominant donor. | Donor diversification strategy as part of the resource mobilisation strategy. | Ongoing |  | ¥ Continuously clarify the comparative advantage of ASARECA 'ss niche and mandate to attract new donors & funding | ¥ Value proposition paper developed: Both corporate level and country.
¥ Develop ASARECA pitch statement and other communication
[6 empty] | ¥ Active engagement of diverse donor sources. | ¥ Implement RMSS action plan
¥ Mapping out potential donors funding the AR4D sector.
¥ Pending development specific donor engagement plans
[6 empty] | ¥ Maintain appropriate reserve balance level to allow for core programme investment | ¥ Updated reserved policy June 2020
¥ Minimum reserve policy of US$ 1.2m
¥ Engagement members to the collection of fees
3 | Failure to follow Approved internal and donor procedures | Possible cancellation of grant agreements | Capacity building of staff on procurement procedures. | 2020-12-01 |  | ¥ Induction & training of all staff on OM provisions | ¥ All staff have access to the current approved OM.
[5 empty] | ED & Head of Finance |  | ¥ Organise capacity building season on a specific section of the OM for all staff
¥ OM study is part of the induction program for new staff.
[6 empty] | ¥ Institutionalise Project launches which include training of staff on donor guidelines and expenditure eligibility criteria | ¥ Ongoing implementation of project launch, which includes all staff and relevant partners
¥ Ensure all relevant staff have access to grant agreements and understand deliverables and reporting commitments
[6 empty] | ¥ Attend external donor organised training to create internal expertise in major donors guidelines and conditionalities for fiduciary and technical staff | ¥ Key staff have attended such events whenever available
¥ Continuous implementation
[6 empty] | ¥ Recruit and retain a qualified fiduciary management team | ¥ Team recruitment is done, including
ü Head of finance
ü Accountant
ü Procurement officer
ü Admin and Personnel officer
¥ This core team reports to and works with the Executive Director and Deputy Executive Director to manage the fiduciary functions of ASARECA
|  | Refund of ineligible expenditures. | Effective monitoring and internal and external, and board oversight audit of the programmes. | Semi-annually | ED & Head of Finance | ¥ Create an independent internal audit function and capacitate the internal audit team | ¥ Audit charter approved by Board in place
¥ Internal auditor in place
¥ Budget and work plan approved by Board.
[6 empty] | ¥ Provide time for and implement timely external audit reviews | ¥ External auditors for 2021 recruited by Sep 2021
¥ Annual audits done and approved by Board
[6 empty] | ¥ Put in place regular quality internal reporting, including progress reports to Management, Board of Directors & donors | ¥ Periodic Board reports done at least bi-annually, latest December 2020 at 30th Board
¥ EXCO and other committees meet regularly
¥ Monthly management reports at PMG meetings
[6 empty] | ¥ Develop reporting compliance checklists | ¥ Procurement checklist
¥ pending subgrantees.
[6 empty] | ¥ Developed a cost allocation policy | ¥ Cost allocation policy in place
|  | Loss of reputation affects future ability to attract funding | Clear policies on operations | Dec 2020 and ongoing | Head of Finance | ¥ Donor engagement on key policies and procedures | ¥ OM presented to majors donors for due diligence and no objection approvals(e.g. WB 2018, IFAD 2020)
[6 empty] | ¥ Seek “no-objection” approvals in advance of material transactions and manage risk cost ineligibility | ¥ No objection sought as per donor agreement, for example:
i. AWPB
[5 empty] | all managers |  | ii. Auditor appointment
iii. Procurement plans
iv. Major transaction
v. Key staff Recruitment etc.
[6 empty] | ¥ Ensure OM is updated regularly to include best practices and carry out regular sensitisation processes for staff on OM and major donor guidelines | ¥ Comprehensive periodic update of OM.
¥ Lasted updated comprehensively in Dec 2018,
¥ Limited update in august 2020
¥ ongoing – expected approval by Q4 2021
[6 empty] | ¥ Institutionalise a zero-tolerance culture for fraud. | ¥ Annual sign off on code of contract done for 2021
[6 empty] | ¥ All staff annually sign a code of conduct commitment to ethical behaviour | ¥ all staff sanitised on ethical conduct and zero tolerance to fraud
4 | Failure to follow Approved internal and Donor procedures by sub-grantees. | sub-grantees generating ineligible expenses | Competitive selection of subgrantees to eliminate conflict of interest | As and when | Programs | ¥ Update sub-grant making policy to mandate competitive bidding for grants. | ¥ Done OM update of 2018
[5 empty] | Managers | ¥ The sub-grantee agreement must include relevant donor guidelines and conditionalities | ¥ Done OM update of 2018
|  | Failure of enforces refund of ineligible expenditures. | effective due diligence process to access capacity to follow procedures | As and when | Head of Finance | ¥ Develop & mandate the use of a sub-grantee reporting checklist | ¥ Done June 2020
[6 empty] | ¥ Include grant management capacity as criteria for awarding grants. | ¥ Done OM updated.
[5 empty] | Internal auditor |  | ¥ Implementation ongoing.
[6 empty] | ¥ Mandate Internal auditor review as part of sub-grant agreements | ¥ Done OM updated.
¥ Implementation ongoing.
|  | loss of reputation affect future ability to attract funding | training and capacity building investment | Immediately | Head of Finance | ¥ Invest in training on reporting and cost eligibility conditions for all sub-grantees | ¥ Planned for all new sub-grantees
|  |  | Enforceable MOUs and subgrantee contracts |  |  |  | ¥ All sub granting agreements are reviewed by a legal advisor to ensure enforceability
[6 empty] | ¥ Design legally enforceable sub-grantee agreements with appropriate Legal advice. | ¥ Ongoing August 2020
|  |  | Effective monitoring oversight over sub-grantees | As and when | Programs | ¥ Develop and include monitoring budget in all projects | ¥ Planned for all grants
[5 empty] | Managers |  | ¥ Included in all new sub-grantee awards
[6 empty] | ¥ Schedule multi-disciplinary team sub-grantee monitoring visits as part of the annual work plans | ¥ Planned for all new subgrantee awards
[6 empty] | ¥ Digital archive & hard paper filling system installed to keep supporting documents at the secretariat | ¥ Design of filling systems consultancy completed Q1 2021
¥ Road map to digitisation designed
¥ Procurement for digitisation pending budget allocation TBC by Q4 2021
5 | Failure to comply with laws and regulation | Operating license/ host agreement withdraw leading to going concern issues | Ongoing monitoring of Compliance requirements | Annual | Head of Finance | ¥ Develop & deploy a legal compliance checklist for the host country and other operating countries. | ¥ Legal advisor completed 2020
¥ Periodic review (preferably Annual) should be required
[5 empty] | Internal auditor | ¥ Include legal compliance checks in all audits | ¥ Legal compliance is a key element of audits
¥ Management and Board, therefore, is regularly updated as part of the internal audit reports
|  | Damage of Reputation | Seeking expert advisory services | As and when |  | ¥ Contract legal advisors on a retainer basis for ongoing legal advice legal compliance | ¥ Active Legal advisor contract in place.
[5 empty] | Head of Finance |  | ¥ Periodic review and renewal processes annually
|  | Fines and penalties leading to financial loss | Capacity building of team responsible for compliance | Annual | ED & | ¥ Sensitise staff and Board on compliance obligations | ¥ The legal team consulted on an ongoing basis
[5 empty] | Legal advisors | ¥ Institute regular compliance reports to management and BoD | ¥ The legal team attend BoD meeting & give real-time advice on the legality of board decisions
|  |  | Strategic engagement with statutory regulatory bodies | As and when | ED | ¥ Institute regular engagement visits to line ministries | ¥ Visits to line miniseries are Ongoing, especially for Uganda, where ASARECA has a host agreement.
¥ Other countries line-ministers visits coordinated with both DGs and Board members resident in the respective countries
¥ Visits are also planned by management with HLAP or as part of country-level activities.
[6 empty] | ¥ Engage statutory bodies on regulatory issues | ¥ Regular engagement with statutory bodies like Tax authorities (URA), Ministry of Finance for Tax and legal advisor e.t.c
¥ Updated returns for Tax, social security etc.
¥ Any other agencies as needed, e.g. labour office etc.
[6 empty] | ¥ Active involvement in host government MOFA activities | ¥ Active contact with protocol office
¥ Periodically Invited protocol office to engage with the Board at induction.
¥ Update protocol office on changes and status of the diplomatic team
¥ Register and be part of the MOFA mailing list for regular events and updates
¥ Ensure an ASARECA representative attends MOFA events whenever invited
6 | Political risk | A radical change in Government policy/structure constraining ASARECA's Programme | Strategic engagement with the relevant member government | Annual | ED/ Board | ¥ Use the regular CPM Summits as an accountability platform for national commitments to ASARECA | ¥ CPM held in 2019
¥ Planned in 2022
[6 empty] | ¥ Regional programming focus on reducing the negative impact of political instability in any one location/country | ¥ Projects are designed with a regional focus. For example;
i. CAAPD XP4 cover 6 core countries
ii. AIRREA – project cover 3 countries
i. AICCRA PROJECT Cover ?? core countries
ii. WAC –Water Management Facility Project cover ?? countries
i. WATDEV Cover 4 Core Countries
¥ Ongoing implementation for all new project development which is both multi-county and also multi-partner.
[6 empty] | ¥ Member engagement, strategic communication and reporting on impact to keep stakeholders engaged | ¥ Ongoing/continuous
[6 empty] | (monthly newsletters, annual corporate reports, publications e.g. ASARECA@25, social media, etc.) | ¥ Consultative meeting of B.o.D, DGs and PSs of line ministries held Oct 2020
¥ Engage DGs, HLAP and other members on strategies for timely fees collection.
¥ Ongoing collection activities including selected advocacy visits to member countries by ASARECA management
|  | Political instability, especially in the Host country resulting in insecurity for staff and Assets. | Effective monitoring of risk to allow for proactive risk management | Annual | Board and ED | ¥ Install cloud-based operation tools & systems to allow remote operation | ¥ Cloud server hosting for business support system installed.
¥ Key: mail, K-HUB, M&E, Office 365, One drive, TIMPs, Website etc.
¥ Tools: Zoom, Teams, online banking & transaction processing etc.
¥ Pending: online Financial accounting system and online digital filling
[5 empty] | H.o.F | ¥ Develop and invest in a business continuity plan | ¥ To Complete Q4 2021
[6 empty] | ¥ Invest in risk transfer tools like insurance to cover loss of assets | ¥ Insurance policies in place for
GPA, Staff Medical and Travel, All risks for Assets. e.t .c
¥ Professional indemnity insurance for both Board and senior management
¥ Ongoing annual renewals
[5 empty] | Board and ED | ¥ Maintain constitutional flexibility on host country options which allows Secretariat transfer in case of Host country hostility | ¥ Constitutionally provided for. (2019 continuation)
¥ Ongoing monitoring of political Situation.
|  | The conflict between member states constraining ASARECA's regional operations | Capacity building of staff, especially in strategic communication | Semi-annual | ED | ¥ Maintain constitutional flexibility on host country options which allows secretariat transfer | ¥ Constitutionally provided for. (2019 continuation)
¥ Ongoing monitoring of political Situation
[6 empty] | ¥ Use the periodic CPM Summits as an accountability platform for national commitments to ASARECA | ¥ CPM held in 2019
¥ Planned in Sept 2021
7 | Failure to attract & retain appropriate talent | Skills gap | Resource mobilisation enhances the ability to put in place a competitive offering | Annual | ED | ¥ Offer competitive remuneration to staff: perform periodic salary survey to inform remuneration policy | ¥ Done in 2018
¥ Planned Q4 2021
[6 empty] | ¥ Develop Volunteer Policy to attract skilled volunteers and Recruit additional staff to fill identified Gaps | ¥ Volunteer guidelines developed by 2019
¥ Volunteers sourced as needed. There is ongoing procurement of:
i. Communication assistant
ii. Finance assistant
ii. Procurement assistant
ii. Thematic leads
|  | Limited staff numbers leading to stifling of operations | Capacity building of staff and leveraging on the skill base on the member organisations | Ongoing | ED | ¥ Invest in programme monitoring systems to give real-time feedback on delivery progress and quality | ¥ M& E system updated and enhanced for online and real-time report generation
¥ Field data collection is ongoing to be up to date by Jan 2022
[6 empty] | ¥ Put in place a Peer review mechanism between ASARECA, other SROs and NARs to keep a reputation for quality programming | ¥ Partially done:
¥ CAADP steering and advisory committees.
¥ Committee of DGs operationalised as a forum for peer review, quality assurance and technical advisory space to ASARECA work.
¥ Committee of NFPs
|  | Loss of reputation, funding and inability to deliver on the mandate | Build skills database within NARs to use as a resource to complement the Secretariat team in programme delivery | 2020-12-01 | Head of Finance | ¥ | ¥
[6 empty] | ¥ Develop skills database and policy to guide cost-sharing of skills with NARIs | ¥ Compilation of Skills database on going Dec Q4 2021
[6 empty] | ¥ Continue review and update of the OM chapters on programme design and approaches to ensure best practices | ¥ Comprehensive periodic update of OM.
¥ Lasted updated comprehensively in Dec 2018,
¥ Limited update in august 2020
¥ Ongoing – expected approval by Q4 2021
8 | Asset mismanagement | Refund of ineligible expenditures. | Capacity building of staff on Asset management | 2020-12-01 | Procurement Officer | ¥ Organise training for staff on procurement and disposal procedures | Training done
¥ Contract management
¥ Proposal evaluation
¥ Others scheduled for 2021
|  | Loss of assets | Effective monitoring and internal and external, and board oversight audit of the programmes. | Annual | Head of Finance | ¥ Regularly update asset register and carry out annual asset verification exercises | ¥ Register updated periodically (at least annually)
[6 empty] | ¥ Asset audits as part of regular organisational audits | ¥ Asset audits are done annually by both internal and external auditors
|  | loss of reputation | Clear policies on operations | Annual | Head of Finance | ¥ Clarify the Identification and Disposal of all assets as per procurement policy | ¥ Updated as per fixed asset register
¥ OM updated to clarify policy by Q4 2021
9 | Service contract mismanagement |  | Capacity building of staff on procurement and contract management procedures. | Annual | Procurement Officer | ¥ Put in place clear contract management procedures | ¥ OM up to date on contract management procedures
|  | Poor delivery by contractors leading to Possible cancellation of grant agreements |  |  |  |  | ¥ Staff Team trained on contract management
[6 empty] | ¥ Use of the competitive procurement processes that ensure value for money | ¥ OM up to date with competitive procurement procedures
|  | Litigation risk and finical loss | Active and effective contract monitoring, both internal and external, and board oversight. | As and when | ED | ¥ Develop standard legally enforceable contracts for service providers | ¥ Use of standard legal contract in place
¥ Contracts are bench-marked against WB approved formats.
[6 empty] | ¥ Designate contract managers with clear roles and responsibilities for each contract | ¥ Contract managers are designated for each contract
¥ Roles and responsibilities included in the OM
|  | loss of reputation affects funding | Put in place legal advisory for contracts | As and when | ED | ¥ Appoint legal advisor on a retainer basis | ¥ Active Legal advisor contract in place.
¥ Periodic review and renewal processes annually Done
10 | information security | Unauthorised access to organisation systems leading to loss of data and system failure. | Investment in up to date physical and logical controls | 2020-12-01 | ICT Consultant | ¥ Review and update information & Communication policy | ¥ Information retention policy developed Feb 2021
¥ Filling system for all documents put in place (One-drive).
[6 empty] | ¥ Update security and logical controls regularly | Improved security with documents moved to the cloud as below
¥ Public and departmental shared folders set up on the cloud storage.
¥ Principle of least privilege applied onto all documents on the cloud storage (People access only what they are authorised to);
¥ Audit logs on whoever has accessed network resources.
¥ Periodic updates to the systems to fix any security loopholes;
¥ Encouraging staff to change their passwords quarterly basis;
¥ Periodical pieces of training on new tools that can help everyone work better;
¥ Registering and authenticating devices access our network;
¥ Bi-Annual servicing of all ASARECA computer and Network hardware and resources.
¥ Renewal of expired licenses
|  | Could lead to financial loss | Effective monitoring and internal and external information security | Annual | Internal Auditor | ¥ Carry out annual information security audits | ¥ Pending information security audit scheduled as part of the audit work plan 2021
|  | reputation damage affects future ability to attract funding | Clear policies on data and information management | Immediately | Head of Finance | ¥ Develop and implement standard data disposal policies | ¥ Information retention policy developed 2021 update with OM update process
11 | Major Accidents and disasters | A major disruption in working arrangements | Investment in appropriate risk monitoring, financing and risk transfer tools | Immediately | ED | ¥ Staff training on disaster risk awareness | ¥ Internal training on risk management done March 2021
¥ Regularly hold staff Joint review of the risk mitigation action plans
¥ Regular report to the Board on risk mapping and mitigation activities
¥ Training on the use of firefighting equipment Sept 2021
[5 empty] | HoF | ¥ Install cloud-based remote working tools | ¥ Procure cloud-based MS 365 license
¥ Procure and install cloud server for documents and website
¥ License and install remote working tools like zoom and MS Teams.
¥ Transfer other business systems like M&E
¥ Plans to transfer Accounting and develop digital filing systems 2022.
¥ Carry out user training for staff done in 2021
To be completed by an ICT consultant in Q4 2021
¥ Continue to develop the capacity to hold remote work in place.
[6 empty] | ¥ Put appropriate insurance policies in place | ¥ Insurance policies in place for
GPA, Staff Medical and Travel, All risks for Assets. e.t .c
¥ Generate proposal for Professional Indemnity Insurance for both Board and senior management submit to ED office for consideration by Sept 2021
¥ Ongoing annual renewals
|  | Loss of productive assets and staff safety challenges | Effective Business Continuity and Disaster Recovery Planning | Immediately | ED & ICT Consultant | ¥ Business Continuity & Disaster recovery plans (DRP) | ¥ Ongoing work to develop a DRP To be completed Q4 2021
[6 empty] | ¥ Appropriate budget and investment in the DRP | ¥ Budget for and implement DRP 2022
|  | Suspension of the funding streams due to economic slowdown in donor countries | Maintain appropriate reserve balances | Immediately | Head of Finance | ¥ Update reserve policy | ¥ Completed and approved June 2021
[6 empty] | ¥ Maintain reserve balance appropriate for fixed and investment in a minimum core programming level | ¥ Updated reserved policy June 2020
[6 empty] | ¥ Consider raising annual membership fees by member States | ¥ Minimum reserve policy of US$ 1.2m
[6 empty] | ¥ Implement fees collection from other members than NARIs | ¥ Plan to increase membership fees approved by 30th Board to move from $15,000 to $50,000 in 2022.
¥ Continue with Registration of members and partners beyond 2021
¥ Implement individualised membership fees collection strategies
12 | Loss of Mandate | Loss of member support | Periodic strategic review and re-alignment | After every 5 year | BoD/ED | ¥ Periodic consultative Strategy reviews (Every 5 years) | ¥ Strategy review completed Dec 2018
[6 empty] | ¥ CPM Summit every two years | ¥ CPM held May 2019 & CPM planned 2021
[6 empty] | ¥ Regular Committee of DGs meetings | ¥ Bi-annual CDGs meetings institutionalised with a recent meeting held in June 2021
|  | Inability to raise funding | Active engagement of members and other stakeholders | Annual | ED | ¥ Ongoing membership engagement, including at CPM | ¥ Consultative meeting of B.A.Ed., DGs and PSs of line ministries held Oct 2020
[6 empty] | ¥ Consider raising annual membership fees by member States | ¥ Engage DGs, HLAP and other members on strategies for timely fees collection.
[6 empty] | ¥ Implement fees collection from other members other than NARIs | ¥ Ongoing collection activities including selected advocacy visits to member countries by ASARECA management
[6 empty] | ¥ New member registration and admission | ¥ Membership registration is done in 2021 plan to recruit new core members implemented
¥ 2 new country members joined in 2011 Continuous member engagement
[6 empty] | ¥ Strategic communication for members (monthly newsletters, annual corporate reports, publications e.g. ASARECA@25, social media, etc.) | ¥ Monthly newsletters sent out to up to 2000 recipients
¥ Annual Cooperate report out for 2020
¥ Publication ASARECA@25 in December 2020
|  | Going concern risks | Ensure the relevance of strategic choices to members needs | Every 5 years | ED | ¥ Periodic consultative Strategy reviews (Every 5 years) | ¥ Strategy review completed Dec 2018
[6 empty] | ¥ Regular meetings of Committee of DGs meetings | ¥ CPM held May 2019 & CPM planned in 2021
[6 empty] | ¥ Regular CPM Summits | ¥ Bi-annual CDGs meetings institutionalised with a recent meeting held in June 2021
¥ Permanent engagement with RCEs
13 | Governance Failure | Conflict of interest at the governance level | Governance system review and renewal. | Every 5 years | BoD/ED | ¥ Independent periodic governance reviews (Every 5 years) | ¥ Review scheduled in 2025
[6 empty] | ¥ Constitution and governance manual revisions | ¥ Periodic review of governance documents latest update done May 2019
|  | Damage to organisation reputation & possible litigation and going concern issues | Operationalise internal accountability mechanisms as per governance manual | Annual | BoD/ED | ¥ Develop Board renewal/rotation plan by Board nomination & governance standing committee | ¥ Board meetings have a standing Legal on hand to ensure Board decisions comply with the law, Constitution, Governance Manuals & OM
[6 empty] | ¥ Implement regular Board of Director rotations between members, RECs and relevant sectors | ¥ Board renewal is part of the standing agendas at the Governance and nominations committee of the Board to ensure accountability oversight.
[6 empty] | ¥ Ensure diversity of skills within Board members | ¥ Skills diversity requirement is part of the board recruitment criteria
[6 empty] | ¥ Board member performance appraisal evaluation Annually | ¥ Latest Board Self-appraisal approved at the 30th Board in December 2020
¥ Next Due in Q4 of 2021
|  | Inadequate board oversight over management | Organise governance training for Board | Annual | BoD/ED | ¥ Implement New board member induction programs | ¥ Induction institutionalised for all new Board members & Continuous
¥ All Board members have access to governance policies and strategies.
[6 empty] | ¥ Maintain a member representative board with skill diversity of the Board | ¥ Members of BoD drawn from members & Continuous
¥ Identify external training capacity building providers and recommend attendance of board members.
¥ In June 2021, Audit committee chair Dr Yona Baguma attended training by the Uganda institute of internal auditors on Board oversight roles